## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Brandon | 6500 | 950 | 5550 | 2500 | 300 | 2200 | 2500 | 550 | 1950 | 1500 | 100 | 1400
Josh | 12100 | 550 | 11550 | 8300 | 0 | 8300 | 2500 | 550 | 1950 | 1300 | 0 | 1300
Lucas | 6500 | 550 | 5950 | 2700 | 0 | 2700 | 2500 | 550 | 1950 | 1300 | 0 | 1300
Sheldon | 6000 | 400 | 5600 | 2200 | 0 | 2200 | 2500 | 400 | 2100 | 1300 | 0 | 1300
Connor | 5400 | 550 | 4850 | 1600 | 0 | 1600 | 2500 | 550 | 1950 | 1300 | 0 | 1300
Jubal | 5000 | 350 | 4650 | 1200 | 0 | 1200 | 2500 | 350 | 2150 | 1300 | 0 | 1300
Total | 41500 | 3350 | 38150 | 18500 | 300 | 18200 | 15000 | 2950 | 12050 | 8000 | 100 | 7900

## Gantt
| Predicted Time(hrs) | Time Spent(hrs) | key: |  | completed |  |  | this week |  |  | planned
Brandon |  |  | hours: | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81
gantt chart creation | 3 | 3
track health / progress | 5 | 0
user interface | 10 | 0
pickup items | 4 | 0
placeholder | 0 | 0
placeholder | 0 | 0
testing | 3 | 0
totals | 25 | 3
Josh
logo creation | 3 | 0
model Animation | 5 | 0
player character modeling | 5 | 0
object / environment assets model | 30 | 0
object / asset animations | 20 | 0
placeholder | 0 | 0
placeholder | 0 | 0
testing | 20 | 0
totals | 83 | 0
Lucas
programming - AI | 10 | 0
Sound Implementation | 5 | 0
level design | 3 | 0
mini map | 5 | 0
placeholder | 0 | 0
testing | 4 | 0
totals | 27 | 0
Sheldon
menu design | 6 | 0
programming ship controls | 4 | 0
User Customizable Input | 2 | 0
Implementing menu | 4 | 0
placeholder | 0 | 0
testing | 6 | 0
totals | 22 | 0
Connor
setup GIT Hub | 1 | 0
collision detection | 10 | 0
create unity project | 1 | 0
placeholder | 0 | 0
placeholder | 0 | 0
testing | 4 | 0
totals | 16 | 0
Jubal
coding standard creation | 2 | 0
level design (2) | 5 | 0
placeholder | 0 | 0
placeholder | 0 | 0
placeholder | 0 | 0
testing | 5 | 0
totals | 12 | 0
group totals (hrs) | 185 | 3
group totals ($) | 18500 | 300

## Meetings
| Date | Jan. 24 | Feb. 3 | Feb. 5 | DATE | DATE | DATE | DATE | DATE | DATE | DATE
| Purpose | First Meeting | RFP / Game Planning | SA Presentation Planning / RFP Preparation | Future Meeting | Future Meeting | Future Meeting | Future Meeting | Future Meeting | Future Meeting | Future Meeting
| Hours | 1.5 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brandon | 5.5 | ü | ü | ü
Josh | 5.5 | ü | ü | ü
Lucas | 5.5 | ü | ü | ü
Sheldon | 4 |  | ü | ü
Connor | 5.5 | ü | ü | ü
Jubal | 3.5 | ü | ü
Totals | 29.5 | 7.5 | 12 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Brandon | Individual schedule | 2 | 0 | bar: 1 to 2
| Champion | 5 | 0 | bar: 7 to 11
| Writing RFP | 4 | 0 | bar: 3 to 6
| Merge Gantt Charts | 2 | 1 | bar: 12 to 13
| Assemble SA Powerpoint | 2 | 0 | bar: 14 to 15
| Subtotal | 15 | 1
Josh | Individual schedule | 2 | 0 | bar: 1 to 2
| Champion | 5 | 0 | bar: 7 to 11
| Writing RFP | 4 | 0 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 0 | bar: 12 to 13
| Subtotal | 13 | 0
Lucas | Individual schedule | 2 | 0 | bar: 1 to 2
| Champion | 5 | 0 | bar: 7 to 11
| Writing RFP | 4 | 0 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 0 | bar: 12 to 13
| Subtotal | 13 | 0
Sheldon | Individual schedule | 2 | 0 | bar: 1 to 2
| Champion | 5 | 0 | bar: 7 to 11
| Writing RFP | 4 | 0 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 0 | bar: 12 to 13
| Subtotal | 13 | 0
Connor | Individual schedule | 2 | 0 | bar: 1 to 2
| Champion | 5 | 0 | bar: 7 to 11
| Writing RFP | 4 | 0 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 0 | bar: 12 to 13
| Subtotal | 13 | 0
Jubal | Individual schedule | 2 | 0 | bar: 1 to 2
| Champion | 5 | 0 | bar: 7 to 11
| Writing RFP | 4 | 0 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 0 | bar: 12 to 13
| Subtotal | 13 | 0
| Total | 80 | 1
red is dependent on others