## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Brandon | 6500 | 3450 | 3050 | 2700 | 1200 | 1500 | 2500 | 950 | 1550 | 1300 | 1300 | 0
Josh | 12000 | 4350 | 7650 | 8300 | 2200 | 6100 | 2500 | 950 | 1550 | 1200 | 1200 | 0
Lucas | 6700 | 2050 | 4650 | 3000 | 200 | 2800 | 2500 | 750 | 1750 | 1200 | 1100 | 100
Sheldon | 5900 | 2700 | 3200 | 2200 | 800 | 1400 | 2500 | 800 | 1700 | 1200 | 1100 | 100
Connor | 5300 | 2150 | 3150 | 1600 | 200 | 1400 | 2500 | 750 | 1750 | 1200 | 1200 | 0
Jubal | 4900 | 850 | 4050 | 1200 | 100 | 1100 | 2500 | 350 | 2150 | 1200 | 400 | 800
Total | 41300 | 15550 | 25750 | 19000 | 4700 | 14300 | 15000 | 4550 | 10450 | 7300 | 6300 | 1000

## Gantt
| Predicted Time(hrs) | Time Spent(hrs) | key: |  | completed |  |  | this week |  |  | planned
Brandon |  |  | hours: | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81
gantt chart creation | 3 | 3
track health changes | 6 | 4
track time changes | 3 | 2
user interface setup | 12 | 3
placeholder | 0 | 0
placeholder | 0 | 0
testing | 3 | 0
totals | 27 | 12
Josh
logo creation | 3 | 2
player character modeling | 5 | 3
model Animation | 5 | 2
object / environment assets model | 30 | 10
object / asset animations | 20 | 5
placeholder | 0 | 0
placeholder | 0 | 0
testing | 20 | 0
totals | 83 | 22
Lucas
background music | 5 | 1
UI sounds | 2 | 1
entity effects | 3 | 0
terrain effects | 2 | 0
demo/AI | 15 | 0
testing | 3 | 0
totals | 30 | 2
Sheldon
menu design | 6 | 4
programming ship controls | 4 | 2
User Customizable Input | 2 | 2
Implementing menu | 4 | 0
placeholder | 0 | 0
testing | 6 | 0
totals | 22 | 8
Connor
setup GIT Hub | 1 | 1
collision detection | 10 | 0
create unity project | 1 | 1
placeholder | 0 | 0
placeholder | 0 | 0
testing | 4 | 0
totals | 16 | 2
Jubal
coding standard creation | 2 | 1
level design (2) | 5 | 0
placeholder | 0 | 0
placeholder | 0 | 0
placeholder | 0 | 0
testing | 5 | 0
totals | 12 | 1
group totals (hrs) | 190 | 45
group totals ($) | 19000 | 4500

## Meetings
| Date | Jan. 24 | Feb. 3 | Feb. 5 | DATE | DATE | DATE | DATE | DATE | DATE | DATE
| Purpose | First Meeting | RFP / Game Planning | SA Presentation Planning / RFP Preparation | Finalized RFP and Presentation | Initial Demo Prep / Game start | Future Meeting | Future Meeting | Future Meeting | Future Meeting | Future Meeting
| Hours | 1.5 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
Brandon | 9.5 | ü | ü | ü | ü | ü
Josh | 9.5 | ü | ü | ü | ü | ü
Lucas | 7.5 | ü | ü | ü | ü
Sheldon | 8 |  | ü | ü | ü | ü
Connor | 7.5 | ü | ü | ü | ü
Jubal | 3.5 | ü | ü
Totals | 45.5 | 7.5 | 12 | 10 | 10 | 6 | 0 | 0 | 0 | 0 | 0
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Brandon | Individual schedule | 2 | 1 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Writing RFP - 1.0, 8.0, 9.0, 10.0 | 3 | 3 | bar: 3 to 6
| Merge Gantt Charts | 1 | 1 | bar: 12 to 13
| Assemble SA Powerpoint | 2 | 4 | bar: 14 to 15
| Subtotal | 13 | 13
Josh | Individual schedule | 2 | 1 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Writing RFP - 5.0, 6.0 | 3 | 3 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 4 | bar: 12 to 13
| Subtotal | 12 | 12
Lucas | Individual schedule | 2 | 1 | bar: 1 to 2
| Champion | 5 | 3 | bar: 7 to 11
| Writing RFP - 2.0, 4.0, 7.0, 10.0 | 3 | 3 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 4 | bar: 12 to 13
| Subtotal | 12 | 11
Sheldon | Individual schedule | 2 | 1 | bar: 1 to 2
| Champion | 5 | 3 | bar: 7 to 11
| Writing RFP - 2.0, 3.0, 5.0, 10.0 | 3 | 3 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 4 | bar: 12 to 13
| Subtotal | 12 | 11
Connor | Individual schedule | 2 | 1 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Writing RFP - 2.0 | 3 | 3 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 4 | bar: 12 to 13
| Subtotal | 12 | 12
Jubal | Individual schedule | 2 | 1 | bar: 1 to 2
| Champion | 5 | 3 | bar: 7 to 11
| Writing RFP - TBD | 3 | 0 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 0 | bar: 12 to 13
| Subtotal | 12 | 4
| Total | 73 | 63
red is dependent on others